## Task list
Legend
Low Priority
Medium Priority
High Priority
Completed Task
Timeline
Task | People | Priority | Start Date | End Date | Days Left | Status | Relative Start Day | Task Duration in Days | January | March | June
Concept Design IPA Pump | All | High | 2019-01-01 | 2019-02-01 | -127 | Completed | 0 | 31
Purchase DAQs and Pressure Transducers | Tim, Julio | Low | 2019-02-01 | 2019-02-07 | -121 | Completed | 31 | 6
Purchase Tachometer and Temperature Sensor | Julio | Low | 2019-02-01 | 2019-02-07 | -121 | Completed | 31 | 6
Purchase Flow Meter | Julio | Medium | 2019-02-01 | 2019-02-07 | -121 | Completed | 31 | 6
Finalize Shaft & Impeller CAD | Phil | Low | 2019-02-01 | 2019-02-08 | -120 | Completed | 31 | 7
IPA Pump Prototyping | Jonas, Nick | Medium | 2019-01-26 | 2019-02-15 | -113 | Completed | 25 | 20
Finish machining impeller / shaft for open tank testing | Nick, Jonas, Shayli | High | 2019-01-21 | 2019-02-25 | -103 | Completed | 20 | 35
Run open tank test | All | Medium | 2019-02-01 | 2019-02-28 | -100 | Completed | 31 | 27
Motor Selection | Phil, Julio | Medium | 2019-02-16 | 2019-03-01 | -99 | Completed | 46 | 13
IPA Shaft & Impeller Material Selection | Henry, Nick | Medium | 2019-02-16 | 2019-03-01 | -99 | Completed | 46 | 13
Finalize CAD designs based on open tank test results | Phil | Medium | 2019-02-28 | 2019-03-22 | -78 | Completed | 58 | 22
Finish Progress Report - Winter Term | All | Low | 2019-02-01 | 2019-03-15 | -85 | Completed | 31 | 42
Begin FEA Analysis for LOX Pump | Nick, Julio | Medium | 2019-02-16 | 2019-04-12 | -57 | Completed | 46 | 55
Test IPA Rev 1 | All | High | 2019-03-07 | 2019-04-23 | -46 | Incomplete | 65 | 47
Concept Design LOX Pump | All | High | 2019-01-01 | 2019-04-12 | -57 | Completed | 0 | 101
Control System Design | Julio, Nick | Medium | 2019-01-01 | 2019-04-19 | -50 | Completed | 0 | 108
Manufacturing IPA Pump | Jonas, Nick, Shayli | High | 2019-02-15 | 2019-04-19 | -50 | Completed | 45 | 63
Control System Testing | All | High | 2019-03-07 | 2019-04-19 | -50 | Completed | 65 | 43
Testing IPA Pump | All | Medium | 2019-03-07 | 2019-04-23 | -46 | Completed | 65 | 47
Testing LOX Pump | All | Medium | 2019-04-21 | 2019-05-07 | -32 | Completed | 110 | 16
Full System Test | All | High | 2019-05-07 | 2019-05-21 | -18 | Completed | 126 | 14
Creating Github Repo for PSAS | Phil | Medium | 2019-04-01 | 2019-06-01 | -7 | Completed | 90 | 61
Final Write Up | All | Low | 2019-04-01 | 2019-06-15 | 7 | Completed | 90 | 75
System Demonstration | All | Low | 2019-06-07 | 2019-06-15 | 7 | Incomplete | 157 | 8
IPA Test #2 | All | High | 2019-05-09 | 2019-05-16 | -23 | Completed | 128 | 7
Manufacturing LOX Pump | Jonas, Nick, Shayli | High | 2019-05-06 | 2019-05-20 | -19 | Completed | 125 | 14
Mounting Case Manufacturing | Jonas, Shayli, Nick | Medium | 2019-05-06 | 2019-05-20 | -19 | Completed | 125 | 14
Capstone Poster Design | Shayli | Medium | 2019-05-06 | 2019-05-25 | -14 | Completed | 125 | 19